## Sheet1
Tasks(Weekly Plans)	Who	% Complete	Time est.	Time Spent	Review
Create TPS report in LibreOffice	M / T	25 50 75 100	30 mins.	45 mins.
Setup repository on github	M / T	25 50 75 100	1 hr.	30 mins.
Research IEEE floating point	M / T	25 50 75 100	4 hrs.	1 hr.
Find a coding style	M / T	25 50 75 100	30 mins.	1 hr.
Research Build standards	M / T	25 50 75 100	1 hr.	30 mins.
Compiling programs of basic solutions	M / T	25 50 75 100	20 mins.	30 mins.
Finding build standards document- make	M / T	25 50 75 100	5 mins.	5 mins.
Setting up build environment – / directories, makefiles, bash script for / coverage testing makefiles	M / T	25 50 75 100	2 hrs.	2 hrs.
Researching .md extension for READMEs / Adding README template	M / T	25 50 75 100	30 mins.	30 mins.
Creating READMEs	M / T	25 50 75 100	15 mins.	15 mins.
Researching solutions better than basic / Solutions	M / T	25 50 75 100	2 hrs.	2 hrs.
	M / T	25 50 75 100
	M / T	25 50 75 100
	M / T	25 50 75 100
	M / T	25 50 75 100
	M / T	25 50 75 100